## Product Backlog Template
Product owner want to make an Application to calculate "Daily Wage" for co-workers
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
| Create Account: | As a customer I Create Account so I can sign in | High | yes | 1 | Complete
| Category | As a customer I want the user to define it person as a (Co-worker, supervisor or accountant ) | High | yes | 1 | Complete
| Add to Cart: | If the user "co-worker), As a customer I want the co-worker enter his card details to be able to transfetr money | High | yes | 1 | Complete
| Sign in: | As a customer I want to enter my data | High | yes | 2 | Ongoing
| Resgister starting hour | As a customer I want the co-worker enter the starting hour | High | no | 2 | planned
| Register ending hour | As a customer I want the co-worker enter the ending hour | High | no | 2 | planned
| Approval by supervisor | As a customer I want the Supervisor | Medium | no | 3 | planned
| Calculate the working hours | As a customer i want the to calaculate the working hour and daily wage | High | yes | 3 | Ongoing
| "Daily wage" approval | As a customer I want the accountant aprove to transfer money | Medium | yes | 4 | Ongoing
| Forget Password: | As a User I forget password so that I reset it | Medium | no | 4 | planned